## Assumptions
Municipal Citizen Request Platform — Development Budget
Lean Estimation — Scrum Methodology ¦ Story Points & Velocity-Based Budget
A. TEAM & RATE ASSUMPTIONS (blue cells = inputs you can change)
| Role | # People | Weekly Rate (USD) | Sprint Weeks | Sprint Cost (USD) | Notes
| Project Manager | 1 | 1800 | 2 | 3600 | Scrum Master / PM hybrid
| Frontend Developer | 2 | 1600 | 2 | 6400 | React – Citizen Portal & Admin
| Backend Developer | 3 | 1700 | 2 | 10200 | Node/Python microservices
| DevOps / Cloud Engineer | 1 | 1900 | 2 | 3800 | AWS/Azure, CI/CD
| QA Engineer | 1 | 1400 | 2 | 2800 | Manual + automated testing
| UI/UX Designer | 1 | 1500 | 2 | 3000 | Part-time, first 4 sprints only
| TOTAL SPRINT COST (per sprint) |  |  |  | 29800
B. VELOCITY & SPRINT ASSUMPTIONS
| Sprint duration (weeks) | 2 | Fixed 2-week sprints
| Team velocity (story pts/sprint) | 40 | After ramp-up; first sprint 30 SP
| Total story points (backlog) | 234 | See Backlog sheet for detail
| Buffer / contingency (%) | 15% | 15% for unknowns & rework
C. DERIVED BUDGET OUTPUTS
| Number of sprints (base) |  |  | 6
| Number of sprints (w/ buffer) |  |  | 7
| Project duration (weeks) |  |  | 14
| BASE LABOR COST |  |  | 178800
| TOTAL BUDGET (w/ buffer) |  |  | 208600
| Technology & Licenses / yr |  |  | 10548
| GRAND TOTAL (Labor + Tech) |  |  | 219148

## Backlog
Agile Product Backlog — Municipal Citizen Request Platform
# | Epic | User Story | As a… | Priority | SP | Sprint | Acceptance Criteria (summary) | Status
1 | EP1 Authentication & SSO | US-01 Citizen registration | Citizen | Must Have | 5 | 1 | Email verified; duplicate check; password policy enforced | Pending
2 |  | US-02 Citizen login (email/pwd) | Citizen | Must Have | 3 | 1 | JWT issued; locked after 5 failed attempts | Pending
3 |  | US-03 Password recovery | Citizen | Must Have | 3 | 1 | Reset link expires in 1hr; new password saved securely | Pending
4 |  | US-04 Staff SSO via Gov. Identity Provider | Admin/Staff | Must Have | 8 | 2 | SSO redirects to Gov IdP; session token valid 8hrs | Pending
5 |  | US-05 Role-based access control | Admin/Staff | Must Have | 5 | 2 | Citizen / Staff / Supervisor roles enforced at API level | Pending
6 | EP2 Citizen Request Portal | US-06 Submit new service request | Citizen | Must Have | 8 | 2 | Request saved with unique ID; confirmation shown | Pending
7 |  | US-07 Attach photos / documents | Citizen | Must Have | 5 | 3 | Files <10MB accepted; stored in S3; preview shown | Pending
8 |  | US-08 Geolocate request on map | Citizen | Must Have | 8 | 3 | Map renders; lat/lng stored; address auto-populated | Pending
9 |  | US-09 View request status & history | Citizen | Must Have | 5 | 3 | Timeline shows all status changes with timestamps | Pending
10 |  | US-10 Receive email notification on update | Citizen | Must Have | 5 | 4 | Email sent within 2 min of status change | Pending
11 |  | US-11 Receive SMS notification | Citizen | Should Have | 3 | 4 | SMS sent via Twilio within 2 min | Pending
12 |  | US-12 Search & filter my requests | Citizen | Should Have | 3 | 4 | Filter by status, date range, category; results <1s | Pending
13 | EP3 Admin Dashboard | US-13 View all incoming requests | Admin/Staff | Must Have | 5 | 2 | Paginated list; sortable columns; real-time refresh | Pending
14 |  | US-14 Assign request to department | Admin/Staff | Must Have | 8 | 3 | Dropdown of departments; assignment logged with timestamp | Pending
15 |  | US-15 Update request status | Admin/Staff | Must Have | 5 | 3 | Status options: Open / In-Progress / Resolved / Closed | Pending
16 |  | US-16 Add internal comments to request | Admin/Staff | Must Have | 3 | 3 | Comment visible only to staff; audit trail kept | Pending
17 |  | US-17 Filter & search requests by type/dept/status | Admin/Staff | Should Have | 5 | 4 | Multi-filter; URL-shareable state; <500ms response | Pending
18 |  | US-18 View resolution time KPIs | Admin/Staff | Should Have | 8 | 5 | Charts: avg resolution time, open vs closed, by dept | Pending
19 |  | US-19 Export requests to CSV/Excel | Admin/Staff | Could Have | 3 | 6 | CSV export reflects current filters; <5s for 10k rows | Pending
20 | EP4 Reporting & Analytics | US-20 Generate performance report | Admin/Staff | Should Have | 8 | 5 | PDF report generated; date-range selectable | Pending
21 |  | US-21 Dashboard charts (requests by type/dept) | Admin/Staff | Should Have | 8 | 5 | Bar/pie charts; monthly trend line; filters applied | Pending
22 |  | US-22 Avg. resolution time per department | Admin/Staff | Should Have | 5 | 5 | Table grouped by dept; sortable; benchmark column | Pending
23 |  | US-23 Export report as PDF | Admin/Staff | Could Have | 5 | 6 | PDF matches screen; auto-paginated; branded header | Pending
24 | EP5 Notification Service | US-24 Email notification on request creation | Citizen | Must Have | 3 | 4 | Triggered on creation; template personalised with ID | Pending
25 |  | US-25 Email digest for staff (daily summary) | Admin/Staff | Should Have | 5 | 5 | Daily 8AM digest; summarises new + overdue requests | Pending
26 |  | US-26 SMS alert for critical request types | Citizen | Could Have | 5 | 6 | High-severity categories trigger SMS within 5 min | Pending
27 | EP6 File Upload Service | US-27 Upload images up to 10 MB | Citizen | Must Have | 5 | 3 | Progress bar; error shown if >10MB; S3 key returned | Pending
28 |  | US-28 Validate file type (jpg, png, pdf) | Citizen | Must Have | 3 | 3 | Reject unsupported MIME types with clear error message | Pending
29 |  | US-29 Store files in S3 Object Storage | System | Must Have | 5 | 3 | Files stored under /requests/{id}/; pre-signed URLs | Pending
30 |  | US-30 Admin can download attachments | Admin/Staff | Must Have | 3 | 4 | Download link available in request detail; audit logged | Pending
31 | EP7 Infra & DevOps | US-31 Setup CI/CD pipeline (GitHub Actions) | DevOps | Must Have | 8 | 1 | Pipeline: lint → test → build → deploy on merge to main | Pending
32 |  | US-32 Configure cloud hosting (AWS/Azure) | DevOps | Must Have | 8 | 1 | VPC, subnets, security groups configured; SSL cert applied | Pending
33 |  | US-33 Setup PostgreSQL & Redis | DevOps | Must Have | 5 | 1 | DB schema migrated; Redis cluster reachable from services | Pending
34 |  | US-34 Configure S3 + IAM roles | DevOps | Must Have | 5 | 2 | Bucket policy: private; roles scoped to least privilege | Pending
35 |  | US-35 Monitoring & alerting (logs/metrics) | DevOps | Should Have | 8 | 6 | Alerts for >1% 5xx errors and >500ms p95 latency | Pending
36 |  | US-36 Load balancer & auto-scaling | DevOps | Should Have | 8 | 6 | Auto-scale triggers at 70% CPU; tested under load | Pending
37 | EP8 QA & Testing | US-37 Unit tests (>80% coverage) – Auth Service | QA | Must Have | 5 | 2 | Jest/Pytest; CI fails if coverage drops below 80% | Pending
38 |  | US-38 Integration tests – API Gateway | QA | Must Have | 5 | 3 | Postman/Newman collection; all endpoints tested | Pending
39 |  | US-39 E2E tests – citizen submission flow | QA | Must Have | 8 | 4 | Playwright script; passes on Chrome, Firefox, Safari | Pending
40 |  | US-40 Load testing (500 concurrent users) | QA | Should Have | 8 | 6 | k6 test; p95 latency <800ms at 500 users | Pending
41 |  | US-41 Accessibility audit (WCAG 2.1) | QA | Could Have | 5 | 7 | axe-core scan; 0 critical/serious violations | Pending
42 |  | US-42 Security pen-test & vulnerability scan | QA | Must Have | 8 | 7 | OWASP ZAP scan; no high/critical findings in report | Pending
TOTAL STORY POINTS |  |  |  |  | 234

## Sprint Plan
Sprint Plan & Timeline — Municipal Request Platform
Sprint | Weeks | Focus / Theme | Key Stories | SP Target | Cum. SP | Labor Cost (USD)
Sprint 1 | Wk 1-2 | Foundation & Infra | US-31,32,33 CI/CD, Cloud, DB setup; US-01,02,03 Auth basics | 32 | 32 | 29800
Sprint 2 | Wk 3-4 | Auth & Core Backend | US-04,05 SSO/RBAC; US-06 Request submission; US-13 Admin list; US-34,37 | 36 | 68 | 29800
Sprint 3 | Wk 5-6 | Citizen Portal MVP | US-07,08,09 Upload/Map/Status; US-14,15,16 Admin ops; US-27,28,29,38 | 52 | 120 | 29800
Sprint 4 | Wk 7-8 | Notifications & Refinement | US-10,11,12 Notifications; US-17,24,30 Filters & downloads; US-39 E2E tests | 30 | 150 | 29800
Sprint 5 | Wk 9-10 | Analytics & Reporting | US-18,20,21,22 KPIs & charts; US-25 Staff digest | 34 | 184 | 29800
Sprint 6 | Wk 11-12 | Operations & Hardening | US-19,23,26 Exports; US-35,36 Monitoring/scaling; US-40 Load test | 37 | 221 | 29800
Sprint 7 | Wk 13-14 | UAT & Go-Live Prep | US-41,42 Accessibility & security; regression testing; prod deployment | 13 | 234 | 29800
TOTAL |  |  |  | 234 | 1009 | 208600

## Tech Costs
Technology & Licensing Costs — Annual Estimate
Category | Service / Tool | Plan / Tier | Monthly Cost (USD) | Annual Cost (USD) | Notes
Cloud Hosting | AWS EC2 / Azure VM (t3.medium × 4) | On-demand | 480 | 5760 | Estimate; varies with usage
Cloud Hosting | AWS RDS PostgreSQL (db.t3.medium) | Multi-AZ | 90 | 1080 | Estimate; varies with usage
Cloud Hosting | AWS ElastiCache Redis (cache.t3.sm) | Single node | 25 | 300 | Estimate; varies with usage
Cloud Hosting | AWS S3 Object Storage (500 GB/mo) | Standard | 12 | 144 | Estimate; varies with usage
Cloud Hosting | AWS ALB Load Balancer | Standard | 22 | 264 | Estimate; varies with usage
3rd Party APIs | SendGrid Email API | Essentials | 20 | 240 | Estimate; varies with usage
3rd Party APIs | Twilio SMS | Pay-as-you-go | 30 | 360 | Estimate; varies with usage
3rd Party APIs | Google Maps API | Pay-as-you-go | 50 | 600 | Estimate; varies with usage
3rd Party APIs | Government SSO (IdP) | Public/free | 0 | 0 | Estimate; varies with usage
DevOps & Tools | GitHub (Actions + repos) | Team plan | 40 | 480 | Estimate; varies with usage
DevOps & Tools | Monitoring (Datadog / CloudWatch) | Pro | 80 | 960 | Estimate; varies with usage
DevOps & Tools | Domain & SSL certificate | Annual | 5 | 60 | Estimate; varies with usage
Security | AWS WAF | Standard | 20 | 240 | Estimate; varies with usage
Security | AWS Secrets Manager | Standard | 5 | 60 | Estimate; varies with usage
ANNUAL TECHNOLOGY TOTAL |  |  |  | 10548

## Budget Summary
Development Budget Summary — Municipal Request Platform
| Total Story Points | Sprints Required | Project Duration | Team Size
| 234 | 7 | 14 | 9
BUDGET BREAKDOWN
Category | Detail | Low Estimate (USD) | Base Estimate (USD) | High Estimate (USD) | % of Total
Labor — Development | 7 sprints × full team | 177310 | 208600 | 238400 | 77.08%
Technology & Cloud | Annual infra + 3rd-party APIs | 8438.4 | 10548 | 12657.6 | 3.898%
QA & Security Audit | External pentest + tools | 3000 | 3500 | 5000 | 1.293%
Contingency (15%) | Buffer for scope changes & rework | 17731 | 31290 | 47680 | 11.56%
Project Management | PM overhead & stakeholder meetings | 10430 | 16688 | 23840 | 6.166%
GRAND TOTAL |  | 216909.4 | 270626 | 327577.6 | 100%
KEY ASSUMPTIONS • Rates are in USD; team based in Latin America (competitive market rates). • 2-week sprints; velocity of 40 SP/sprint after initial ramp-up (Sprint 1 = 30 SP). • Technology costs are estimated annual figures; actual cloud usage may vary. • 15% contingency applied to labor for scope changes and rework. • Government SSO integration assumes a standard SAML 2.0 / OpenID Connect endpoint is provided at no cost. • Fixed-scope model: backlog is prioritized; if budget is constrained, 'Could Have' stories are deferred.